## Plan
задача | описание | исполнитель | длительность | предшественники | id | start_date | end_date
Product Discovery | Clarify MVP scope, personas, and success metrics. | Maya Chen | 3 |  | task-01 | 2026-10-05 | 2026-10-07
Architecture Spike | Domain model, MCP boundary, scheduling approach. | Alex Rivera | 3 | Product Discovery | task-04 | 2026-10-08 | 2026-10-10
UX Wireframes | Low-fidelity flows for planner, Gantt, and chat. | Maya Chen | 4 | Product Discovery | task-02 | 2026-10-08 | 2026-10-11
API Contract | REST endpoints and Plan/Task DTO schema. | Alex Rivera | 2 | Architecture Spike | task-05 | 2026-10-11 | 2026-10-12
UI Design System | Visual language for Gantt bars, chat, and modals. | Sofia Berg | 5 | UX Wireframes | task-03 | 2026-10-12 | 2026-10-16
Domain Model & PlanService | Canonical mutations, validation, draft transactions. | Alex Rivera | 4 | API Contract | task-06 | 2026-10-13 | 2026-10-16
Frontend Scaffold | Vite React TypeScript app shell and routing. | Sofia Berg | 3 | UI Design System | task-12 | 2026-10-17 | 2026-10-19
MCP Tool Layer | Typed MCP tools wrapping PlanService mutations. | Alex Rivera | 4 | Domain Model & PlanService | task-10 | 2026-10-17 | 2026-10-20
Scheduler Engine | Deterministic FS scheduling and cycle detection. | Jordan Lee | 3 | Domain Model & PlanService | task-07 | 2026-10-17 | 2026-10-19
Backend API | FastAPI routes for plan, tasks, import/export, chat. | Jordan Lee | 5 | Scheduler Engine | task-08 | 2026-10-20 | 2026-10-24
Excel Import/Export | Parse and write xlsx compatible with planner columns. | Jordan Lee | 3 | Backend API | task-09 | 2026-10-25 | 2026-10-27
Gantt Chart UI | Interactive Gantt bound to plan state. | Sofia Berg | 5 | Backend API, Frontend Scaffold | task-13 | 2026-10-25 | 2026-10-29
LLM Agent Loop | Chat turn orchestration with tool calling. | Alex Rivera | 4 | Backend API, MCP Tool Layer | task-11 | 2026-10-25 | 2026-10-28
Excel UI Actions | Import/export buttons and error toasts. | Maya Chen | 2 | Excel Import/Export, Frontend Scaffold | task-16 | 2026-10-28 | 2026-10-29
Integration Tests | API, scheduler, MCP, and Excel roundtrip tests. | Sam Okonkwo | 4 | Backend API, Excel Import/Export, MCP Tool Layer | task-17 | 2026-10-28 | 2026-10-31
AI Chat Panel | Right-rail chat UI wired to /api/chat. | Maya Chen | 4 | LLM Agent Loop, Frontend Scaffold | task-15 | 2026-10-29 | 2026-11-01
Task Detail Modal | View and edit task fields from Gantt click. | Sofia Berg | 2 | Gantt Chart UI | task-14 | 2026-10-30 | 2026-10-31
E2E Smoke Demo | Seed → import → chat mutation → export path. | Sam Okonkwo | 3 | Gantt Chart UI, AI Chat Panel, Excel UI Actions, Integration Tests | task-18 | 2026-11-02 | 2026-11-04
Deployment Packaging | Dockerfile, compose, env samples, README runbook. | Jordan Lee | 2 | E2E Smoke Demo | task-19 | 2026-11-05 | 2026-11-06
Demo Rehearsal | Walkthrough script and polish for assignment review. | Maya Chen | 2 | Deployment Packaging | task-20 | 2026-11-07 | 2026-11-08